## Sheet1
Date | Day | StartTime | EndTime | Minutes | Description
2023-05-17 | Wednesday | 14:00 | 15:00 | 60 | Components arrived: - Planned out how I am going to connect everything together - Soldered the pins of my RFID MFRC522
2023-05-20 | Saturday | 11:00 | 16:30 | 330 | - Tried to get the TFT Display working and testing ~ Found a library to work with the display but still figuring out how to use the display with this library
2023-05-21 | Sunday | 11:00 | 16:30 | 330 | - Understood how to use the Display with the library - Tried to run the the RFID MFRC522 to test Note: I was able to get the RFID running alone but unfortunately I ran into an issue where the RFID uses SPI pins but the Display connects to all the SPI pins on the Mega - Set up the state machines needed for the project, including the Joystick
2023-05-21 | Sunday | 18:00 | 23:00 | 300 | - Tried to connect the RFID through UART and I2C ~ Both were not able to work - Decided to try daisy chain with the SPI pins ~ Planning to solder some wires to the SPI pins on top of the display
2023-05-22 | Monday | 14:00 | 17:00 | 180 | - Soldered some wires on the pins on top of the display ~ Took me forever as I had trouble soldering wire to wire so I got help later
2023-05-23 | Tuesday | 18:00 | 23:00 | 300 | - Connected and tested to have the Joystick move around a string on the Display - Connected the RFID to print something on the Display when a valid scan is made
2023-05-26 | Friday | 12:00 | 13:00 | 60 | - Made a new arduino file - Set up state machines for the joystick and rfid scan
2023-05-27 | Saturday | 11:00 | 16:00 | 300 | - Finished making tic-tac-toe game as it's own state machine from scratch (Only have PvP currently made)
2023-05-28 | Sunday | 11:00 | 16:00 | 300 | - Added PvAI for tic-tac-toe - Debugged some extreme case scenarios with movement - Set up the states in a new state machine for Snake
2023-06-03 | Saturday | 11:00 | 14:30 | 210 | - Finished the snake game and debugged a few errors related to out of bounds